## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Laguar Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000274/2020-2021 | 1418/RD/PHE | 11/12/2020 | 10/01/2021 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 10.53 | 10.33 | 98.03 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Habipur Mouza under Amalbari and Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000272/2020-2021 | 1420/RD/PHE | 11/12/2020 | 10/01/2021 | SANJIB BHATTACHARJEE | 10.54 | 9.98 | 94.71 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Sahasra Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000273/2020-2021 | 1419/RD/PHE | 11/12/2020 | 10/01/2021 | LOKENATH CO-OP LBOUR CONTRACT &CONSTRUCTION SOCIETY LTD. | 10.56 | 10.37 | 98.13 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002089/2021-2022 | 772/W | 11/03/2022 | 11/03/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Baldoria Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000292/2020-2021 | 1440/RD/PHE | 11/12/2020 | 10/01/2021 | DIPANKAR SARKAR | 10.56 | 10.48 | 99.23 | 1
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Amalbari Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000275/2020-2021 | 1417/RD/PHE | 11/12/2020 | 10/01/2021 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 10.56 | 10.48 | 99.26 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) at Ranipur Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000276/2020-2021 | 467/RD/PHE | 26/02/2021 | 28/03/2021 | M/S BHOWMIK ENTERPRISE | 10.53 | 10.37 | 98.53 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 1.49 | 30.98 | 100
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 15.01.2025 to 14.07.2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000808/2024-2025 | 298/RD/PHE | 15/01/2025 | 15/07/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.4 | 0.22 | 9.27 | 60
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block | SM/07073 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 11-03-2025, 12-03-2025,18-03-2025 and 21-03-2025. |  |  | BILL/01391/2025-2026 | 8443117 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
Total | [13 empty] | 70.64 | 63.72 | 90.2