## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme | SM/07139 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under FARIDPUR and ADJOINING Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000468/2020-2021 | 1413/ RD | 11/12/2020 | 20/01/2021 | M/S MAA TARA CONSTRUCTION BIRNAGAR SUNILPRAMAICK1961@GMAIL.COM | 67.94 | 14.76 | 21.73 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme | SM/07139 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000523/2024-2025 | 95/RD/PHE | 08/01/2025 | 08/07/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0.4 | 16.55 | 100
Total | [13 empty] | 70.34 | 15.16 | 21.55