## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Majhiali Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000130/2020-2021 | 1426/RD/PHE | 11/12/2020 | 10/01/2021 | S.B.CONSTRUCTION | 16.48 | 15.17 | 92.05 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Dakshin Kundal Pukur Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000263/2020-2021 | 1428/RD/PHE | 11/12/2020 | 10/01/2021 | M/S BHOWMIK ENTERPRISE | 16.5 | 15.2 | 92.13 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Ariagaon Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000264/2020-2021 | 1427/RD/PHE | 11/12/2020 | 10/01/2021 | CHAITANYA SAMAL | 17.17 | 20.77 | 120.96 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Uttar Besarbari Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000262/2020-2021 | 1429/RD/PHE | 11/12/2020 | 10/01/2021 | IDEAL CO-OP LABOUR CONTRACT &CONST SOCIETY LTD. | 16.94 | 9.37 | 55.32 | 1
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002106/2021-2022 | 752/W | 11/03/2022 | 11/03/2022 | JHUNU SAHA | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002092/2021-2022 | 753/W | 11/03/2022 | 11/03/2022 | SAHA CONSTRUCTION | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 26/06/2024 | MD ZAFAR EQUEBAL | 4.8 | 1.53 | 31.93 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme | SM/07140 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 10-03-2025,17-03-2025, 26-03-2025 and 28-03-2025. |  |  | BILL/01383/2025-2026 | 8443119 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
Total | [13 empty] | 72.19 | 62.05 | 85.95