## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme | SM/07141 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Pawakhali and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000260/2020-2021 | 1415/RD/PHE | 11/12/2020 | 20/01/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 76.67 | 29.88 | 38.97 | 100
Total | [13 empty] | 76.67 | 29.88 | 38.97