## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme | SM/07141 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Pawakhali and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000260/2020-2021 | 1415/RD/PHE | 11/12/2020 | 20/01/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 76.67 | 29.88 | 38.97 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme | SM/07141 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000523/2024-2025 | 95/RD/PHE | 08/01/2025 | 08/07/2025 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0.8 | 33.15 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme | SM/07141 | Retrofitting | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (Period for 15/01/2025 to 14/07/2025) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000811/2024-2025 | 300/RD/PHE | 15/01/2025 | 15/07/2025 | SISIR KUMAR DUTTA | 2.4 | 0.23 | 9.38 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme | SM/07141 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. (Period for 15/07/2025 to 14/01/2026). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000215/2025-2026 | 2068/RD/PHE | 14/07/2025 | 14/01/2026 | SISIR KUMAR DUTTA | 2.4 | 1.24 | 51.84 | 85
Total | [13 empty] | 83.87 | 32.14 | 38.32