## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Butijhari and Adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000271/2020-2021 | 1412/RD/PHE | 11/12/2020 | 20/01/2021 | SANYAL ENTERPRISE | 86.29 | 38.15 | 44.22 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002094/2021-2022 | 754/W | 11/03/2022 | 11/03/2022 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
Total | [13 empty] | 86.38 | 38.15 | 44.17