## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Butijhari and Adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000271/2020-2021 | 1412/RD/PHE | 11/12/2020 | 20/01/2021 | SANYAL ENTERPRISE | 86.29 | 38.15 | 44.22 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002094/2021-2022 | 754/W | 11/03/2022 | 11/03/2022 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. period from 08/07/205 to 07/01/2026. | Assistant Engineer ISD | Junior Engineer, RWS | ORD/000222/2025-2026 | 2011/RD/PHE | 08/07/2025 | 08/01/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 1.1 | 46.01 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.07.2025 to 14.01.2026). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000217/2025-2026 | 2070/RD/PHE | 14/07/2025 | 14/01/2026 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 2.13 | 88.56 | 50
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 21-02-2025, 24-02-2025, 25-02-2025 and 13-03-2025 |  |  | BILL/01386/2025-2026 | 844394 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 20-03-2025 |  |  | BILL/01387/2025-2026 | 844397 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | You are requested to arrange vehicle with fuel for the below mentioned works of Raiganj Division,PHE Dte. on 03-03-2025 and submit bill (in triplicate) along with challan. |  |  | BILL/01384/2025-2026 | 8443120 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.06 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 24-03-2025 and 25-03-2025 |  |  | BILL/01385/2025-2026 | 844393 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 25-02-2025,07-03-2025 and 25-03-2025. |  |  | BILL/01388/2025-2026 | 844396 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.08 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 03-03-2025 |  |  | BILL/01390/2025-2026 | 8443123 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.06 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 20-02-2025 |  |  | BILL/01366/2025-2026 | 844395 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme | SM/07142 | Retrofitting | Work order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E Dte. on 10-02-2025 |  |  | BILL/01389/2025-2026 | 844382 | 27/03/2026 | 27/03/2026 | DULAL MAJUMDER | 0.1 | 0 | 0 | 0
Total | [13 empty] | 91.86 | 41.38 | 45.05