## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme | SM/07143 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Purba Mohanpur and Khowaspur Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000250/2020-2021 | 1431/RD/PHE | 11/12/2020 | 10/01/2021 | M/S PIONEER ENTERPRISE | 24.17 | 3.12 | 12.91 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme | SM/07143 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002088/2021-2022 | 770/W | 11/03/2022 | 11/03/2022 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme | SM/07143 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Jotilamat and Purba Pipla Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000251/2020-2021 | 1430/RD/PHE | 11/12/2020 | 10/01/2021 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 22.06 | 12.41 | 56.24 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme | SM/07143 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C. vehicle no. WB58CB7128) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. period from 08/07/205 to 07/01/2026. | Assistant Engineer ISD | Junior Engineer, RWS | ORD/000222/2025-2026 | 2011/RD/PHE | 08/07/2025 | 08/01/2026 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 2.4 | 0 | 0 | 0
Total | [13 empty] | 48.72 | 15.53 | 31.87