## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Unatiagachh Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000235/2020-2021 | 1424/RD/PHE | 11/12/2020 | 10/01/2021 | RAHUL ENTERPRISE | 10.45 | 0.99 | 9.45 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Madhya Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000253/2020-2021 | 1423/RD/PHE | 11/12/2020 | 10/01/2021 | NIMAI DAS | 10.93 | 5.85 | 53.54 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Dehar Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000255/2020-2021 | 1436/RD/PHE | 11/12/2020 | 10/01/2021 | MAA BICHITRA CONSTRUCTION | 10.43 | 1.63 | 15.62 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002103/2021-2022 | 764/W | 11/03/2022 | 11/03/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Paschim Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000254/2020-2021 | 1422/RD/PHE | 11/12/2020 | 10/01/2021 | KARTICK BISWAS | 11 | 0 | 0 | 10
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Bhindabari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000252/2020-2021 | 1425/RD/PHE | 11/12/2020 | 10/01/2021 | MS SARKAR ENTERPRISE ABDULGHATA | 10.63 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme | SM/07145 | Retrofitting | FHTC OF DEHAR PWSS | Assistant Engineer ISD |  | ORD/000329/2020-2021 | 1425/RD | 11/12/2020 | 10/01/2021 | M/S SARKAR ENTERPRISE | 10.63 | 17.99 | 169.13 | 100
Total | [13 empty] | 64.18 | 26.45 | 41.22