## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Daribhir Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000265/2020-2021 | 1435/RD/PHE | 11/12/2020 | 10/01/2021 | SAMIRAN PODDAR | 11.06 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002101/2021-2022 | 763/W | 11/03/2022 | 11/03/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | OFFICE ACCESSORIES BILL |  |  | VCH/002087/2021-2022 | 769/W | 11/03/2022 | 11/03/2022 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Gangamaila Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000267/2020-2021 | 1439/RD/PHE | 11/12/2020 | 10/01/2021 | AJIT PARMANIK | 10.77 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Phulhar Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000269/2020-2021 | 1438/RD/PHE | 11/12/2020 | 10/01/2021 | M/S P.S ENTERPRISE | 10.94 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Amlijhari Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000266/2020-2021 | 1421/RD/PHE | 11/12/2020 | 10/01/2021 | MAA SHEETALA ENTERPRISE | 11.38 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme | SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Bijekhor Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000268/2020-2021 | 1437/RD/PHE | 11/12/2020 | 01/01/2023 | HAQUE CONSTRUCTION | 11.29 | 0 | 0 | 100
Total | [13 empty] | 55.62 | 0 | 0