## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) | SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-I) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000249/2020-2021 | 1387/RD/PHE | 09/12/2020 | 08/01/2021 | M/S LUCKY CONSTRUCTION | 15.93 | 6.8 | 42.7 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) | SM/07384 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000164/2020-2021 | 369/RD/PHE | 04/02/2021 | 01/03/2021 | MAA TARA CONSTRUCTION | 4.12 | 3.33 | 80.77 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) | SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-III) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000247/2020-2021 | 1389/RD/PHE | 09/12/2020 | 08/01/2021 | M/S HINDUSTHAN CONSTRUCTION | 15.86 | 15.34 | 96.72 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) | SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000248/2020-2021 | 1388/RD/PHE | 09/12/2020 | 08/01/2021 | M/S CHOUDHURY CONSTRUCTION | 15.84 | 15.31 | 96.66 | 1
Total | [13 empty] | 51.75 | 40.78 | 78.8