## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and Banigaon, Phulatti and Lahanda Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000234/2020-2021 | 1392/RD/PHE | 09/12/2020 | 13/01/2021 | PRASANTA DUTTA | 22.35 | 1.51 | 6.75 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000018/2021-2022 | 1223/RD/PHE | 18/06/2021 | 18/07/2021 | DONE ENTERPRISE | 8.83 | 2.81 | 31.88 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Kasidanga Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000211/2020-2021 | 1390/RD/PHE | 09/12/2020 | 08/01/2021 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.15 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1813/RD/PHE | 23/09/2022 |  | Resource Division | 0.97 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-IV) | Assistant Engineer RSD |  | ORD/000021/2021-2022 | 1260/RD/PHE | 25/06/2021 | 25/07/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 6.23 | 6.08 | 97.52 | 10
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | FHTC OF PHULATTI WSS |  |  | ORD/000035/2020-2021 | 1394/RD | 09/12/2020 | 08/01/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 7.56 | 1.29 | 17.13 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Sahapur Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000210/2020-2021 | 1393/RD/PHE | 09/12/2020 | 08/01/2021 | M/S P.S ENTERPRISE | 12.96 | 1.28 | 9.88 | 60
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block | SM/07385 | Retrofitting | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 22/06/2024 | DEBASISH GHOSH | 4.8 | 0 | 0 | 0
Total | [13 empty] | 78.84 | 12.97 | 16.46