## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | SUPPLYING LAYING FITTING OF FHTC OF MAJLISHPUR WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000363/2020-2021 | 1576/RD | 23/12/2020 | 22/01/2021 | DONE ENTERPRISE | 16.14 | 7.45 | 46.16 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Khesra and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000202/2020-2021 | 1525/RD/PHE | 23/12/2020 | 06/02/2021 | UTTAM SAHA | 126.33 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Faridpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000006/2021-2022 | 1211/RD/PHE | 18/06/2021 | 16/09/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Relaying of Pipe Line along embankment of Canal at Churakutti mouza for Functional Household Tap Connection of Majhlishpur Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000345/2021-2022 | 2159/RD/PHE | 12/11/2021 | 12/12/2021 | SAHA CONSTRUCTION | 4.59 | 0 | 0 | 1
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | SUPPLYING LAYING FITTING OF GOAGAON PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000439/2020-2021 | 1513/RD | 23/12/2020 | 22/01/2021 | M/S GHOSH CONSTRUCTION | 7.87 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF MAJLISHPUR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000452/2020-2021 | 1576/ RD | 23/12/2020 | 22/01/2021 | DONE ENTERPRISE | 16.14 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | SUPPLYING FITTING UPVC PIPE FOR PIROJPUR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000448/2020-2021 | 1521/RD | 03/12/2020 | 02/01/2021 | M/S HINDUSTHAN CONSTRUCTION | 14.46 | 0 | 0 | 1
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Intia and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000176/2020-2021 | 1541/RD/PHE | 23/12/2020 | 01/02/2021 | UTTAM SAHA | 90.4 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Allied Works for Construction and driving including vertical load test of 500 mm dia. (4 Piles Group) of Pile and 23mtr. deep in connection with construction of O.H.R. of FARIDPUR Water Supply Scheme under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000347/2021-2022 | 2161/RD/PHE | 12/11/2021 | 12/12/2021 | M/S ROYAL CONSTRUCTION | 4.43 | 0 | 0 | 1
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | office accessories bill |  |  | VCH/000326/2022-2023 | BP-2022-23-27 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.05 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RESOURCE BILL |  |  | VCH/002570/2021-2022 | BP-2021-22-140 | 24/03/2022 | 24/03/2022 | SUBSIDARY AC OF JJM WB ESCROW AC RESOURCE DIV PHE DIR | 37.16 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | office accessories bill |  |  | VCH/000319/2022-2023 | BP-2022-23-30 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PIROJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000216/2020-2021 | 1559/RD/PHE | 24/12/2020 | 22/02/2021 | AJIT PARMANIK | 193.98 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000018/2021-2022 | 1223/RD/PHE | 18/06/2021 | 18/07/2021 | DONE ENTERPRISE | 8.83 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Ghirinigaon Khas and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E.Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000208/2020-2021 | 1532/RD/PHE | 23/12/2020 | 06/02/2021 | SANYAL ENTERPRISE | 122.54 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba-Rampur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000002/2021-2022 | 1207/RD/PHE | 18/06/2021 | 16/09/2021 | M/S LOKENATH CONSTRUCTION | 36.22 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER UDAYPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000280/2020-2021 | 1561/RD/PHE | 24/12/2020 | 22/02/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 138.21 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PIPLAN AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000281/2020-2021 | 1562/RD/PHE | 24/12/2020 | 22/02/2021 | UTTAM SAHA | 144.08 | 0 | 0 | 0
19 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Ghirnigaon Khas Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000431/2021-2022 | 2193/RD/PHE | 17/11/2021 | 17/12/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 88.75 | 0 | 0 | 0
20 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Restoration and Laying of Pipe Line for Functional Household Tap Connections of Biprit Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000451/2021-2022 | 2427/RD/PHE | 31/12/2021 | 30/01/2022 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 4.95 | 0 | 0 | 100
21 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Jujharpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000446/2021-2022 | 2382/RD/PHE | 24/12/2021 | 23/01/2022 | SAHA CONSTRUCTION | 8.32 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Work Order for Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000115/2022-2023 | 1511/RD/PHE | 18/08/2022 | 17/10/2022 | ASHIM CHANDA | 2.45 | 0 | 0 | 0
23 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Udaypur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000280/2022-2023 | 494/RD/PHE | 17/02/2023 | 03/04/2023 | SANKAR DAS | 8.07 | 0 | 0 | 0
24 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Maslandpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000281/2022-2023 | 495/RD/PHE | 17/02/2023 | 03/04/2023 | GOPES SAHA | 6.91 | 0 | 0 | 0
25 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba Chutiakhore Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Chopra, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000007/2021-2022 | 1212/RD/PHE | 18/06/2021 | 16/09/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.01 | 0 | 0 | 50
26 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Goagaon and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000136/2020-2021 | 1535/RD/PHE | 23/12/2020 | 06/02/2021 | ALOK ENTERPRISE | 112.77 | 0 | 0 | 0
27 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Malgaon and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000138/2020-2021 | 1536/RD/PHE | 23/12/2020 | 06/02/2021 | UTTAM SAHA | 110.22 | 0 | 0 | 0
28 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER MAJLISHPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN GOALPOKHER-I BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | Assistant Engineer RSD |  | ORD/000215/2020-2021 | 1558/RD/PHE | 24/12/2020 | 22/02/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 151.59 | 0 | 0 | 0
29 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | FHTC OF KHESRA WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000157/2020-2021 | 1515/RD | 23/12/2020 | 22/01/2021 | MAA BICHITRA CONSTRUCTION | 8.64 | 0 | 0 | 0
30 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000204/2020-2021 | 1538/RD/PHE | 23/12/2020 | 06/02/2021 | M/S SOMNATH KUNDU | 104.31 | 0 | 0 | 90
31 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Wok Order for supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete(1:2:4) in connection with Retrofitting of Functional Household Tap Connection(FHTC) under Majlishpur and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. |  |  | ORD/000478/2020-2021 | 1516/RD/PHE | 23/12/2020 | 22/01/2021 | DONE ENTERPRISE | 16.13 | 0 | 0 | 0
32 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block | SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD | ORD/000270/2020-2021 | 1414/RD/PHE | 11/12/2020 | 20/01/2021 | J.D.J. ENTERPRISE | 88.73 | 0 | 0 | 100
Total | [13 empty] | 1746.97 | 7.45 | 0.43