## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. | SM/07933 | Anganwadi | Extending piped water supply to Anganwadi Centres (AWCs) housed in own building through tap connection for 162 Nos. Anganwadi Centers within the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer RSD | Junior Engineer, RSD | ORD/000022/2021-2022 | 1254/RD/PHE | 24/06/2021 | 23/08/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 215.78 | 291.97 | 135.31 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. | SM/07933 | Anganwadi | Balance Work in connection with arrangement of w/s by Type-IB solar power operated pumping machinery for Anganwadi Centres having no electrical grid power connections and within the command area of PWSS for 162 Nos. AWCs within the District Of Uttar Dinajpur | Assistant Engineer RSD |  | ORD/000057/2023-2024 | 1584/RD/PHE | 02/06/2023 | 02/07/2023 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.46 | 49.46 | 100 | 10
Total | [13 empty] | 265.24 | 341.42 | 128.72