## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Providing functional household Tap connection under Purba Chutiakhor and adjoining Mouzas Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte.¿ |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000128/2020-2021 | 342/RD/PHE | 01/02/2021 | 02/04/2021 | SANYAL ENTERPRISE | 110.45 | 93.62 | 84.77 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Providing functional household Tap connection under Bhojpur and adjoining Mouzas Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000129/2020-2021 | 343/RD/PHE | 01/02/2021 | 02/04/2021 | M/S LOKENATH CONST | 117.62 | 15.1 | 12.84 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Providing functional household Tap connection under Mahua and adjoining Mouzas Water Supply Scheme at Goalpokher-I Block under Raiganj Division, P.H.E. Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000127/2020-2021 | 344/RD/PHE | 01/02/2021 | 02/04/2021 | J.D.J. ENTERPRISE | 150.74 | 75.5 | 50.09 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | office accessories |  |  | VCH/000313/2022-2023 | BP-2022-23-19 | 28/04/2022 | 28/04/2022 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | office accessories bill |  |  | VCH/000317/2022-2023 | BP-2022-23-32 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | office accessories bill |  |  | VCH/000318/2022-2023 | BP-2022-23-31 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | stationary bill |  |  | VCH/000310/2022-2023 | BP-2022-23-17 | 28/04/2022 | 28/04/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Collection of House Hold Details 6 Nos PWSS at Prescribed format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and submission of the same to PHE Dte. in soft copy. | Assistant Engineer RSD |  | ORD/000474/2020-2021 | 148/RD/PHE | 20/01/2021 | 19/02/2021 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 2.63 | 0.9 | 34.39 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Puria Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000013/2021-2022 | 1218/RD/PHE | 18/06/2021 | 16/09/2021 | AJIT PARMANIK | 36.22 | 26.69 | 73.68 | 50
10 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000126/2020-2021 | 362/RD/PHE | 04/02/2021 | 16/03/2021 | UTTAM SAHA | 91.12 | 4.72 | 5.18 | 1
11 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte | SM/07977 | Retrofitting | Retrofitting of FHTC with additional Pipe Line at Purba Chutiyakhore PWSS in Chopra Block in connection with retrofitting of FHTC under 4nos different schemes Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000397/2023-2024 | 2658/RD/PHE | 15/09/2023 | 28/09/2024 | KARTICK BISWAS | 32.47 | 11.86 | 36.53 | 50
Total | [13 empty] | 541.62 | 228.4 | 42.17