## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). | SM/09109 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000421/2021-2022 | 2183/RD/PHE | 17/11/2021 | 17/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 14.39 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). | SM/09109 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000420/2021-2022 | 2182/RD/PHE | 17/11/2021 | 17/12/2021 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 5.53 | 0 | 0 | 0
Total | [13 empty] | 19.93 | 0 | 0