## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). | SM/09111 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000356/2021-2022 | 2137/RD/PHE | 12/11/2021 | 12/12/2021 | UTTAM SAHA | 3.94 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). | SM/09111 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000355/2021-2022 | 2136/RD/PHE | 12/11/2021 | 12/12/2021 | UTTAM SAHA | 3.94 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). | SM/09111 | Retrofitting | office accessories bill |  |  | VCH/000320/2022-2023 | BP-2022-23-29 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.06 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). | SM/09111 | Retrofitting | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000001/2022-2023 | 896/RD/PHED | 20/04/2022 | 27/04/2022 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 0 | 100
Total | [13 empty] | 12.4 | 0 | 0