## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. | SM/09113 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of CHANDDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000423/2021-2022 | 2185/RD/PHE | 17/11/2021 | 17/12/2021 | M/S BHOWMIK CONSTRUCTION | 7.02 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. | SM/09113 | Retrofitting | Vehicle hiring for inspection and monitoring of Augmentation work of Sariabad PWSS under Raiganj sub-division under Raiganj division, PHE Dte. for the period 13.12.2022 to 16.12.2022 |  |  | BILL/00224/2023-2024 | BP-2023-24-77 | 19/07/2023 | 19/07/2023 | DEBASISH GHOSH | 0.04 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. | SM/09113 | Retrofitting |  |  |  | BILL/00361/2023-2024 | BP-2023-24-78 | 19/07/2023 | 19/07/2023 | DEBASISH GHOSH | 0.08 | 0 | 0 | 0
Total | [13 empty] | 7.15 | 0 | 0