## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of JOYHAT Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000424/2021-2022 | 2186/RD/PHE | 17/11/2021 | 17/12/2021 | M/S.BANGARAJ | 7.76 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Joyhat Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000358/2021-2022 | 2139/RD/PHE | 12/11/2021 | 12/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 4.85 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 29.04.2024,30.04.2024, 02.05.2024 and 03.05.2024. | Assistant Engineer HQ | Estimator | ORD/000017/2024-2025 | 1353/RD/PHE | 25/04/2024 | 29/04/2024 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 08.04.2024,09.04.2024, and 12.04.2024 | Assistant Engineer HQ | Estimator | ORD/000020/2024-2025 | 1203/RD/PHE | 06/04/2024 | 09/04/2024 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 22.04.2024 to 26.04.2024 | Assistant Engineer HQ | Estimator | ORD/000018/2024-2025 | 1274/RD/PHE | 19/04/2024 | 24/04/2024 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 15.04.2024 to 19.04.2024. | Assistant Engineer HQ | Estimator | ORD/000019/2024-2025 | 1238/RD/PHE | 12/04/2024 | 17/04/2024 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 01.04.2024 to 05.04.2024 . | Assistant Engineer HQ | Estimator | ORD/000021/2024-2025 | 1160/RD/PHE | 03/04/2024 | 08/04/2024 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 100
8 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 16.08.2023 to 23.08.2023. |  |  | BILL/01173/2023-2024 | BP-2023-24-313 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.12 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 02.05.2023 to 08.05.2023. |  |  | BILL/01167/2023-2024 | BP-2023-24-302 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.09 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 18.09.2023 to 27.09.2023. |  |  | BILL/01165/2023-2024 | BP-2023-24-317 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. |  |  | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 15/04/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 29.09.2023 to 01.10.2023. |  |  | BILL/01166/2023-2024 | BP-2023-24-318 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.04 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 25.08.2023 to 29.08.2023. |  |  | BILL/01176/2023-2024 | BP-2023-24-314 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.07 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 12.06.2023 to 19.06.2023. |  |  | BILL/01170/2023-2024 | BP-2023-24-306 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.09.2023 to 07.09.2023. |  |  | BILL/01164/2023-2024 | BP-2023-24-315 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.09.2023 to 14.09.2023 |  |  | BILL/01163/2023-2024 | BP-2023-24-316 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.07 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.05.2023 to 18.05.2023. |  |  | BILL/01168/2023-2024 | BP-2023-24-303 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 21.06.2023 to 28.06.2023. |  |  | BILL/01171/2023-2024 | BP-2023-24-307 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.12 | 0 | 0 | 0
19 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 22.05.2023 to 30.05.2023. |  |  | BILL/01175/2023-2024 | BP-2023-24-304 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
20 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.06.2033 to 09.06.2023. |  |  | BILL/01169/2023-2024 | BP-2023-24-305 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
21 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.07.2023 to 16.07.2023. |  |  | BILL/01178/2023-2024 | BP-2023-24-309 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
22 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 03.07.2023 to 07.07.2023. |  |  | BILL/01179/2023-2024 | BP-2023-24-308 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.09 | 0 | 0 | 0
23 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.08.2023 to 07.08.2023. |  |  | BILL/01172/2023-2024 | BP-2023-24-311 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.11 | 0 | 0 | 0
24 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 09.08.2023 to 14.08.2023. |  |  | BILL/01174/2023-2024 | BP-2023-24-312 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
25 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. | SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 19.07.2023 to 26.07.2023. |  |  | BILL/01177/2023-2024 | BP-2023-24-310 | 04/03/2024 | 04/03/2024 | ARNAB DUTTA | 0.13 | 0 | 0 | 0
Total | [13 empty] | 15.63 | 0 | 0