## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. | SM/09115 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Sahavita Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000359/2021-2022 | 2140/RD/PHE | 12/11/2021 | 12/12/2021 | M/S P.S. ENTERPRISE | 4.3 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. | SM/09115 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SAHAVITA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000425/2021-2022 | 2187/RD/PHE | 17/11/2021 | 17/12/2021 | TAPAN KUMAR DUTTA | 7.31 | 0 | 0 | 0
Total | [13 empty] | 11.62 | 0 | 0