## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Bindal WSS for installation of FHTC. | SM/09116 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BINDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000426/2021-2022 | 2188/RD/PHE | 17/11/2021 | 17/12/2021 | UTTAM SAHA | 12.9 | 6.19 | 47.94 | 0
Total | [13 empty] | 12.9 | 6.19 | 47.94