## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. | SM/09118 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BARUA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD |  | ORD/000428/2021-2022 | 2190/RD/PHE | 17/11/2021 | 17/12/2021 | M/S P.S. ENTERPRISE | 18.32 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. | SM/09118 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Barua Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD |  | ORD/000360/2021-2022 | 2141/RD/PHE | 12/11/2021 | 12/12/2021 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. | SM/09118 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. |  |  | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 15/04/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
Total | [13 empty] | 23.95 | 0 | 0