## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. | SM/09119 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Sitgram Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000361/2021-2022 | 2142/RD/PHE | 12/11/2021 | 12/12/2021 | M/S ROYAL CONSTRUCTION | 4.85 | 4.78 | 98.54 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. | SM/09119 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SITGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000429/2021-2022 | 2191/RD/PHE | 17/11/2021 | 17/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 11.69 | 11.67 | 99.79 | 0
Total | [13 empty] | 16.54 | 16.45 | 99.42