## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. | SM/09121 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000362/2021-2022 | 2143/RD/PHE | 12/11/2021 | 12/12/2021 | SWAGATA | 4.42 | 3.7 | 83.76 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. | SM/09121 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000430/2021-2022 | 2192/RD/PHE | 17/11/2021 | 17/12/2021 | HAQUE CONSTRUCTION | 6.19 | 5.74 | 92.75 | 0
Total | [13 empty] | 10.61 | 9.44 | 89.01