## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). | SM/09127 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000376/2021-2022 | 2071/RD/PHE | 02/11/2021 | 02/12/2021 | S.B.CONSTRUCTION | 6.49 | 0.49 | 7.5 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). | SM/09127 | Retrofitting | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000753/2021-2022 | 151/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 3.93 | 0.26 | 6.61 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). | SM/09127 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000729/2021-2022 | 425/RD/PHE | 16/02/2022 | 18/03/2022 | S.B.CONSTRUCTION | 6.43 | 0.03 | 0.51 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). | SM/09127 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Lodhon for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000435/2021-2022 | 2197/RD/PHE | 17/11/2021 | 17/12/2021 | NIMAI DAS | 6.42 | 4.98 | 77.57 | 0
Total | [13 empty] | 23.26 | 5.76 | 24.76