## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. | SM/09128 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Mahadevpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000365/2021-2022 | 2146/RD/PHE | 12/11/2021 | 12/12/2021 | M/S ROYAL CONSTRUCTION | 4.85 | 3.91 | 80.67 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. | SM/09128 | Retrofitting | Additional Pipe Line for Retrofitting of Mahadevpur for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000436/2021-2022 | 2198/RD/PHE | 17/11/2021 | 17/12/2021 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.56 | 4.72 | 62.48 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. | SM/09128 | Retrofitting | stationary bill |  |  | VCH/000309/2022-2023 | BP-2022-23-18 | 28/04/2022 | 28/04/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. | SM/09128 | Retrofitting | stationary bill |  |  | VCH/000311/2022-2023 | BP-2022-23-16 | 28/04/2022 | 28/04/2022 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0 | 0
Total | [13 empty] | 12.58 | 8.64 | 68.65