## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). | SM/09129 | Retrofitting | Pipeline work and other ancillary works at Kulavita village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000023/2021-2022 | 1414/RD/PHE | 07/07/2021 | 06/08/2021 | M/S MANDAL ENTERPRISE | 4.82 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). | SM/09129 | Retrofitting | Pipeline work and other ancillary works at Motilal village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000024/2021-2022 | 1415/RD/PHE | 07/07/2021 | 06/08/2021 | M/S DUTTA ENTERPRISE | 4.8 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). | SM/09129 | Retrofitting | Pipeline work and other ancillary works at Magurjan village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000025/2021-2022 | 1416/RD/PHE | 07/07/2021 | 06/08/2021 | DONE ENTERPRISE | 4.3 | 0 | 0 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). | SM/09129 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Mahua for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-IV) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000437/2021-2022 | 2199/RD/PHE | 17/11/2021 | 17/12/2021 | M/S HINDUSTHAN CONSTRUCTION | 25.63 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). | SM/09129 | Retrofitting | Laying of D.I. Pipeline and Ancillary works for improving the FHTC of Mahua Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000185/2022-2023 | 2255/RD/PHE | 22/12/2022 | 11/01/2023 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 1 | 0 | 0 | 100
Total | [13 empty] | 40.55 | 0 | 0