## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Matikunda (Part-I/II) WSS for installation of FHTC. | SM/09130 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Matikunda for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-I) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000450/2021-2022 | 2386/RD/PHE | 24/12/2021 | 23/01/2022 | M/S LUCKY CONSTRUCTION | 7.89 | 5.89 | 74.64 | 0
Total | [13 empty] | 7.89 | 5.89 | 74.64