## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. | SM/09131 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Pawakhali Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000366/2021-2022 | 2147/RD/PHE | 12/11/2021 | 12/12/2021 | M/S P.S. ENTERPRISE | 4.85 | 4.41 | 90.9 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. | SM/09131 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Pawakhali for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000438/2021-2022 | 2200/RD/PHE | 17/11/2021 | 17/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 16.22 | 14 | 86.33 | 0
Total | [13 empty] | 21.07 | 18.41 | 87.38