## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Siripur for installation of FHTC. | SM/09136 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Siripur for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000439/2021-2022 | 2201/RD/PHE | 17/11/2021 | 17/12/2021 | HAQUE CONSTRUCTION | 8.21 | 8.21 | 99.97 | 0
Total | [13 empty] | 8.21 | 8.21 | 99.97