## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Gopalpur for installation of FHTC. | SM/09151 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of GOPALPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000407/2021-2022 | 2110/RD/PHE | 03/11/2021 | 03/12/2021 | DAS CONSTRUCTION COMPANY | 9.22 | 3.72 | 40.33 | 1
Total | [13 empty] | 9.22 | 3.72 | 40.33