## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. | SM/09160 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of KHESRA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000413/2021-2022 | 2116/RD/PHE | 03/11/2021 | 03/12/2021 | KARTICK BISWAS | 15.94 | 15.66 | 98.25 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. | SM/09160 | Retrofitting | office accessories |  |  | VCH/000315/2022-2023 | BP-2022-23-34 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. | SM/09160 | Retrofitting | office accessories bill |  |  | VCH/000314/2022-2023 | BP-2022-23-35 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. | SM/09160 | Retrofitting | office accessories bill |  |  | VCH/000316/2022-2023 | BP-2022-23-33 | 28/04/2022 | 28/04/2022 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
Total | [13 empty] | 16.21 | 15.66 | 96.61