## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Bhatol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000342/2021-2022 | 2070/RD/PHE | 02/11/2021 | 02/12/2021 | JEET CONSTRUCTION | 8.09 | 7.61 | 94.06 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Bhatol and adjoining mouzas water supply scheme in Raiganj Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000728/2021-2022 | 424/RD/PHE | 16/02/2022 | 18/03/2022 | JEET CONSTRUCTION | 7.8 | 7.17 | 92 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | Retrofitting | Route Survey & Preparation of DPR of BHATOL PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000757/2021-2022 | 155/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 3.85 | 3.48 | 90.31 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 31/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 1.89 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. | SM/09170 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1800/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 2.12 | 0 | 0 | 0
Total | [13 empty] | 23.76 | 18.27 | 76.88