## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | Retrofitting | Route Survey & Preparation of DPR of KASBA NM PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000756/2021-2022 | 154/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000376/2021-2022 | 2071/RD/PHE | 02/11/2021 | 02/12/2021 | S.B.CONSTRUCTION | 6.49 | 0 | 0 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000729/2021-2022 | 425/RD/PHE | 16/02/2022 | 18/03/2022 | S.B.CONSTRUCTION | 6.43 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 30/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 1.54 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. | SM/09171 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 1801/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 1.66 | 0 | 0 | 0
Total | [13 empty] | 18.64 | 0 | 0