## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09172 | Retrofitting | Route Survey & Preparation of DPR of KUNORE PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000758/2021-2022 | 156/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 4.14 | 3.72 | 89.97 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09172 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Kunore Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000377/2021-2022 | 2072/RD/PHE | 02/11/2021 | 02/12/2021 | M/S BHOWMIK ENTERPRISE | 8.79 | 8.74 | 99.51 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09172 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 28/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 2.06 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. | SM/09172 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1802/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 2.31 | 0 | 0 | 0
Total | [13 empty] | 17.29 | 12.47 | 72.1