## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000378/2021-2022 | 2073/RD/PHE | 02/11/2021 | 02/12/2021 | SUBHASIS MAJUMDER | 8.77 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | Retrofitting | Route Survey & Preparation of DPR of KASBA -ITAHAR PWSS under PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000759/2021-2022 | 174/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba [Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000731/2021-2022 | 427/RD/PHE | 16/02/2022 | 18/03/2022 | SUBHASIS MAJUMDER | 8.48 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 29/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 2.06 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09173 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1803/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 2.31 | 0 | 0 | 0
Total | [13 empty] | 25.64 | 0 | 0