## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Hemtabad Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000288/2021-2022 | 1824/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.44 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000001/2022-2023 | 896/RD/PHED | 20/04/2022 | 27/04/2022 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 0 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000745/2021-2022 | 484/RD/PHE | 25/02/2022 | 27/03/2022 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.61 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Preparation of Additional DPR For Hemtabad Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Hemtabad PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000179/2022-2023 | 2151/RD/PHE | 07/12/2022 | 14/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1807/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 2.4 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000380/2021-2022 | 2075/RD/PHE | 02/11/2021 | 02/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.93 | 0 | 0 | 1
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. | SM/09175 | Retrofitting | Allied works in connection with retrofitting of FHTC in Hemtabad PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RSD | Estimator | ORD/000383/2023-2024 | 2609/RD/PHE | 13/09/2023 | 12/11/2023 | ASHIM CHANDA | 0.98 | 0 | 0 | 100
Total | [13 empty] | 47.6 | 0 | 0