## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000383/2021-2022 | 2078/RD/PHE | 02/11/2021 | 02/12/2021 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.05 | 8.79 | 97.08 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | Retrofitting | Retrofitting Of Functional Household Tap Connections(FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000734/2021-2022 | 430/RD/PHE | 16/02/2022 | 18/03/2022 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.98 | 8.8 | 98.01 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | Retrofitting | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000753/2021-2022 | 151/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 3.93 | 3.31 | 84.34 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 27/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 2.15 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. | SM/09178 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1804/RD/PHE | 23/09/2022 | 23/09/2022 | Resource Division | 2.41 | 0 | 0 | 0
Total | [13 empty] | 26.52 | 20.9 | 78.81