## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09181 | Retrofitting | Route Survey & Preparation of DPR of LAKHIPUR PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000754/2021-2022 | 152/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 3.38 | 3.19 | 94.39 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09181 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Lakhipur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000386/2021-2022 | 2081/RD/PHE | 02/11/2021 | 02/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 9.01 | 8.37 | 92.95 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09181 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 05/10/2024 | SISIR KUMAR DUTTA | 4.8 | 1.47 | 30.65 | 0
Total | [13 empty] | 17.19 | 13.04 | 75.84