## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Chopra Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Chopra Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000276/2021-2022 | 1829/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 7.39 | 200 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Retrofitting Of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000747/2021-2022 | 486/RD/PHE | 25/02/2022 | 27/03/2022 | M/S LUCKY CONSTRUCTION | 11.46 | 6.6 | 57.57 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000764/2021-2022 | 598/RD/PHE | 11/03/2022 | 10/05/2022 | ASHIM CHANDA | 2.45 | 2.45 | 100 | 1
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000040/2022-2023 | 992/RD/PHED | 05/05/2022 | 04/07/2022 | ASHIM CHANDA | 2.45 | 2.45 | 100 | 1
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000387/2021-2022 | 2082/RD/PHE | 02/11/2021 | 02/12/2021 | M/S LUCKY CONSTRUCTION | 18.64 | 17.57 | 94.27 | 1
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 42/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 0.29 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1815/RD/PHE | 26/09/2022 | 26/09/2022 | Resource Division | 3.26 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. | SM/09182 | Retrofitting | Allied works in connection with retrofitting of FHTC in Chopra PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000237/2025-2026 | 1041/RD/PHE | 02/04/2025 | 01/06/2025 | ASHIM CHANDA | 0.49 | 0 | 0 | 0
Total | [13 empty] | 42.73 | 36.46 | 85.34