## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dharampur -I Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000278/2021-2022 | 1814/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.9 | 2.32 | 80 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000389/2021-2022 | 2084/RD/PHE | 02/11/2021 | 02/12/2021 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 10.59 | 9.06 | 85.54 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharampur Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000739/2021-2022 | 435/RD/PHE | 16/02/2022 | 18/03/2022 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 9.16 | 6.09 | 66.52 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000385/2021-2022 | 2080/RD/PHE | 02/11/2021 | 02/12/2021 | RAHUL ENTERPRISE | 6.95 | 0.4 | 5.74 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 39/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 0.76 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | Allied works in connection with retrofitting of FHTC in Dharampur Zone-I PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ |  | ORD/000380/2023-2024 | 2606/RD/PHE | 13/09/2023 | 12/11/2023 | ASHIM CHANDA | 0.98 | 0.98 | 100 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09184 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. |  |  | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 15/04/2024 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
Total | [13 empty] | 32.12 | 18.85 | 58.69