## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09186 | Retrofitting | Route Survey & Preparation of DPR of GOALPOKHAR PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000752/2021-2022 | 150/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 4.32 | 3.93 | 90.99 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09186 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Goalpukhur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000391/2021-2022 | 2086/RD/PHE | 02/11/2021 | 28/12/2022 | HAQUE CONSTRUCTION | 9.01 | 7.14 | 79.27 | 100
Total | [13 empty] | 13.33 | 11.07 | 83.07