## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09187 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Ramganj Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Islampur Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000283/2021-2022 | 1819/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.37 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09187 | Retrofitting | Preparation of Additional DPR For Ramganj Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Ramganj PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000176/2022-2023 | 2134/RD/PHE | 07/12/2022 | 14/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09187 | Retrofitting | Allied works in connection with retrofitting of FHTC in Ramganj PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ |  | ORD/000386/2023-2024 | 2605/RD/PHE | 13/09/2023 | 12/11/2023 | ASHIM CHANDA | 0.91 | 0 | 0 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09187 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 35/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 6.81 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. | SM/09187 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) Under Ramganj Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000392/2021-2022 | 2087/RD/PHE | 02/11/2021 | 02/12/2021 | M/S J.S.B ASSOCIATE CONSTRUCTION | 28.69 | 0 | 0 | 1
Total | [13 empty] | 41.56 | 0 | 0