## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) Under Khanta[Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000394/2021-2022 | 2089/RD/PHE | 02/11/2021 | 02/12/2021 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 9.46 | 8.98 | 94.9 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Khanta [Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000738/2021-2022 | 434/RD/PHE | 16/02/2022 | 18/03/2022 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 7.34 | 7.09 | 96.67 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | Route Survey & Preparation of DPR of KHANTA PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000755/2021-2022 | 153/RD/PHE | 25/01/2022 | 24/02/2022 | ENVIROTECH SOLUTIONS | 3.02 | 2.97 | 98.24 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 1819/RD/PHE | 28/09/2022 |  | Resource Division | 2.25 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | Allied works in connection with retrofitting of FHTC in Khanta (Rasakhowa) PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ |  | ORD/000387/2023-2024 | 2607/RD/PHE | 13/09/2023 | 12/11/2023 | ASHIM CHANDA | 0.88 | 0.44 | 50 | 100
6 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01221/2023-2024 | BP-2024-25-24 | 24/04/2024 |  | EXECUTIVE ENGINEER PWD ROADS | 2.84 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09189 | Retrofitting | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS |  |  | BILL/01221/2023-2024 | BP-2024-25-24 | 24/04/2024 |  | EXECUTIVE ENGINEER PWD ROADS | 2.84 | 0 | 0 | 0
Total | [13 empty] | 28.61 | 19.47 | 68.06