## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Panjipara Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000280/2021-2022 | 1816/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.3 | 3.29 | 99.62 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | Retrofitting | Preparation of Additional DPR For Panjipara Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Panjipara PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000177/2022-2023 | 2135/RD/PHE | 07/12/2022 | 14/12/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0.78 | 100 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 38/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 3.98 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Panjipara Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000395/2021-2022 | 2090/RD/PHE | 02/11/2021 | 02/12/2021 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.75 | 16.12 | 96.21 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. | SM/09190 | Retrofitting | Allied works in connection with retrofitting of FHTC in Panjipara PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer RSD | Estimator | ORD/000388/2023-2024 | 2608/RD/PHE | 13/09/2023 | 12/11/2023 | ASHIM CHANDA | 0.84 | 0.84 | 100 | 100
Total | [13 empty] | 25.66 | 21.03 | 81.97