## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Kanki-Matiari Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - II Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000281/2021-2022 | 1817/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.6 | 2.49 | 95.95 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000741/2021-2022 | 437/RD/PHE | 16/02/2022 | 18/03/2022 | TAPAN KUMAR MAJUMDER | 2.99 | 2.88 | 96.35 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 37/RD/PHE | 06/01/2022 |  | Resource Division | 1.35 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 1826/RD/PHE | 28/09/2022 |  | Resource Division | 1.17 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. | SM/09191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000396/2021-2022 | 2091/RD/PHE | 02/11/2021 | 02/12/2021 | TAPAN KUMAR MAJUMDER | 5.8 | 5.02 | 86.51 | 50
Total | [13 empty] | 13.9 | 10.39 | 74.74