## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Raghabpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000286/2021-2022 | 1822/RD/PHE | 14/09/2021 | 14/10/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 2.02 | 66.22 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Raghabpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000397/2021-2022 | 2092/RD/PHE | 02/11/2021 | 02/12/2021 | M/S DOLPHIN CONSTRUCTION | 7.63 | 7.39 | 96.77 | 1
3 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Raghabpur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000737/2021-2022 | 433/RD/PHE | 16/02/2022 | 18/03/2022 | M/S DOLPHIN CONSTRUCTION | 7.34 | 7.05 | 96.15 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 32/RD/PHE | 06/01/2022 | 06/01/2022 | Resource Division | 1.78 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. | SM/09192 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 1818/RD/PHE | 28/09/2022 | 28/09/2022 | Resource Division | 2 | 0 | 0 | 0
Total | [13 empty] | 21.8 | 16.46 | 75.49