## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Sinking 2 nos. of Ground Bored wells,(250mm x 150mm X 120mtr) including cost of materials with proper development and necessary yield for ground water based PWSS for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000473/2021-2022 | 49/RD/PHE | 07/01/2022 | 28/01/2022 | M/S SARKAR ENTERPRISE | 16.99 | 0 | 0 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000121/2022-2023 | 1502/RD | 18/08/2022 | 25/08/2022 | JUMBO XEROX | 0.09 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000122/2022-2023 | 1503/RD | 18/08/2022 | 25/08/2022 | JUMBO XEROX | 0.02 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000129/2022-2023 | 1537\RD | 25/08/2022 | 01/09/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Soil Investigation for Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Kanki Matiari W/S Scheme in Goalpukhur-II Block in Uttar Dinajpur District. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000051/2022-2023 | 1238/RD/PHE | 20/06/2022 | 10/07/2022 | MOYTEC | 1.98 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2006/RD/PHE | 16/11/2022 | 16/11/2022 | Resource Division | 10.51 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | xerox bill |  |  | VCH/001765/2022-2023 | BP-2022-23-212 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.1 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | xerox bill |  |  | VCH/001771/2022-2023 | BP-2022-23-206 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.02 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | xerox bill |  |  | VCH/001770/2022-2023 | BP-2022-23-205 | 04/11/2022 | 04/11/2022 | JUMBO XEROX | 0.09 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Kanki Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000254/2022-2023 | 381/RD/PHE | 07/02/2023 | 24/03/2023 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 5.01 | 0 | 0 | 100
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Kanki-Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000248/2022-2023 | 378/RD/PHE | 07/02/2023 | 24/03/2023 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 4.09 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 638/RD/PHE | 23/03/2022 | 23/03/2022 | Resource Division | 8.75 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Construction of Over Head Reservoir(Capacity-250 Cum) of KANKI MATIARI Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000326/2022-2023 | 655/RD/PHE | 03/03/2023 | 29/10/2023 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 77.82 | 0 | 0 | 75
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Laying of Distribution system including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. (PART-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000467/2021-2022 | 50/RD/PHE | 07/01/2022 | 21/02/2022 | HAQUE CONSTRUCTION | 59.72 | 0 | 0 | 100
15 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KANKI MATIYARI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000877/2022-2023 | 2415/MLMD | 26/09/2022 | 25/12/2022 | TARUN KUMAR DEY | 9.24 | 0 | 0 | 100
16 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KANKI MATIYARI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000878/2022-2023 | 2416/MLMD | 26/09/2022 | 25/12/2022 | UTTAM KUMAR GHOSH | 9.27 | 0 | 0 | 100
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Laying Rising Main pipeline interconnection of Tubewells including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur.(PART -A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000472/2021-2022 | 48/RD/PHE | 07/01/2022 | 21/02/2022 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 0.94 | 0 | 0 | 100
18 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Additional Pipe line with construction of Boundary Wall(Head Work) and other ancillary works at Kanki-Matiari Piped Water Supply Scheme in connection with Augmentation of Kanki-Matiari PWSS under Islampur Sub-Division P.H.E. Dte Under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000031/2024-2025 | 1691/RD/PHE | 10/06/2024 | 03/10/2025 | HAQUE CONSTRUCTION | 25.31 | 0 | 0 | 50
19 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kanki Matiari Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 25 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000361/2025-2026 | 2507/RD/PHE | 12/09/2025 | 11/03/2026 | AJIT PRAMANIK | 16.3 | 0 | 0 | 0
20 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. | SM/09985 | Augmentation | FHTC (Functional Household Tap Connection) for Kanki Matiari Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000006/2022-2023 | 1018/RD/PHED | 12/05/2022 | 26/06/2022 | M/S SARKAR ENTERPRISE | 26.8 | 0 | 0 | 100
Total | [13 empty] | 273.16 | 0 | 0