## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Construction of 2 Nos. Tube-Well ( 250mm diameter x 150mmx140 mtr) for Dilwarpur Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000471/2021-2022 | 47/RD/PHE | 07/01/2022 | 28/01/2022 | BHOLA PAUL | 17.54 | 16.58 | 94.51 | 1
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Dilwarpur W/S Scheme in Kaliaganj Block in Uttar Dinajpur District. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000050/2022-2023 | 1237/RD/PHE | 20/06/2022 | 10/07/2022 | BENGAL CO-OP. ENGINEERS' CONSTRUCTION SOCIETY LTD. | 1.99 | 1.97 | 98.97 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000123/2022-2023 | 1512/RD | 22/08/2022 | 29/08/2022 | JUMBO XEROX | 0.09 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | xerox bill |  |  | VCH/001769/2022-2023 | BP-2022-23-207 | 04/11/2022 |  | JUMBO XEROX | 0.09 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site under Augmentation of Dilwarpur Water Supply Scheme at Kaliyaganj Block under Raiganj Division P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000081/2022-2023 | 1534/RD/PHE | 25/08/2022 | 24/09/2022 | M/S CHOUDHURY CONSTRUCTION | 4.23 | 3.97 | 93.7 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of Dilwarpur Pipe Water Supply Scheme in connection with Augmentation at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000209/2022-2023 | 78/RD/PHE | 17/01/2023 | 14/09/2023 | M/S MASCOT CONSTRUCTION KRISHNADITYA06@GMAIL.COM | 84.11 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Dilwarpur Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000778/2022-2023 | 2276/MLMD | 31/08/2022 | 31/08/2023 | SOUMEN ELECTRIC, | 7.56 | 7.24 | 95.76 | 0
8 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Supply & fitting, fixing of three phase actuator operated wafer type butterfly valve at P.H. NO-II Of Dilwarpur Water Supply Scheme in the district of Uttar Dinajpur under Malda Mehanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001004/2022-2023 | 2202/MLMD | 17/08/2022 | 27/08/2022 | SOUMEN ELECTRIC, | 0.96 | 0.96 | 100 | 0
9 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of DILWARPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000777/2022-2023 | 2275/MLMD | 31/08/2022 | 15/10/2022 | SUBRATA SAHA | 7.34 | 7.32 | 99.79 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | FHTC (Functional Household Tap Connection) for Dilwarpur Water Supply Scheme [Augmentation Scheme] in Kaliaganj Block of Uttar Dinajpur District. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000003/2022-2023 | 1015/RD/PHED | 12/05/2022 | 26/06/2022 | BHOLA PAUL | 45.2 | 42.02 | 92.96 | 95
11 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Making compound lighting arrangement with allied works at T/W no. I of Dilwarpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009096) | Assistant Engineer - I |  | ORD/000709/2023-2024 | 2239/MLMD | 18/07/2023 | 16/10/2023 | NIRMAN. | 2.61 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 637/RD/PHE | 23/03/2022 |  | Resource Division | 9.75 | 0 | 0 | 0
13 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 125/RSD/PHE | 10/08/2022 |  | Resource Division | 0.61 | 0 | 0 | 0
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 126/RSD/PHE | 10/08/2022 |  | Resource Division | 0.16 | 0 | 0 | 0
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 1215/RD/PHE | 10/06/2022 |  | Resource Division | 8.56 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dilwarpur Water Supply Scheme(Augmentation of Dilwarpur PWSS) under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity-35 M3/hr. |  |  | ORD/000428/2023-2024 | 3392/RD/PHE | 12/12/2023 | 30/04/2024 | AJIT PRAMANIK | 17.73 | 0 | 0 | 0
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Laying Distribution System for DILWARPUR and its adjoining Mouza Water Supply Scheme at KALIAGANJ Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000482/2021-2022 | 177/RD/PHE | 27/01/2022 | 13/03/2022 | M/S MAA TARA CONSTRUCTION | 119.05 | 104.62 | 87.88 | 100
18 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 17.12.2022 to 15.01.2023. |  |  | BILL/00946/2023-2024 | BP-2023-24-223 | 15/12/2023 |  | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
19 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. | SM/09989 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for DILWARPUR (Augmentation) and its adjoining Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000470/2021-2022 | 46/RD/PHE | 07/01/2022 | 21/02/2022 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.77 | 0.37 | 47.66 | 100
Total | [13 empty] | 328.77 | 185.05 | 56.29