## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000790/2021-2022 | 178/RD /PHE | 27/01/2022 | 26/07/2022 | M/S MAA TARA CONSTRUCTION | 111.99 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 2005/RD/PHE | 16/11/2022 | 16/11/2022 | Resource Division | 17.06 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SITLAGAON (Augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000475/2021-2022 | 51/RD/PHE | 07/01/2022 | 21/02/2022 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.52 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Sinking 2 nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 200mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for SITLAGAON nad its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000476/2021-2022 | 52/RD/PHE | 07/01/2022 | 28/01/2022 | HAQUE CONSTRUCTION | 19.76 | 0 | 0 | 1
5 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Approach Road including earthwork for road at 2nd Tube Well Site of Sitlagaon Piped Water Supply Scheme in connection with Augmentation of Sitalgaon PWSS under Islampur Sub-Division PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000182/2022-2023 | 2252/RD/PHE | 22/12/2022 | 11/01/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.65 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000246/2022-2023 | 376/RD/PHE | 07/02/2023 | 24/03/2023 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 5.03 | 0 | 0 | 100
7 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 640/RD/PHE | 23/03/2022 | 23/03/2022 | Resource Division | 11.38 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | FHTC (Functional Household Tap Connection) for Shitlagaon Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000005/2022-2023 | 1017/RD/PHED | 12/05/2022 | 13/09/2024 | HAQUE CONSTRUCTION | 53.31 | 0 | 0 | 50
9 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Construction of Over Head Reservoir(Capacity-350 Cum) of SITLAGAON Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000386/2022-2023 | 738/RD/PHE | 15/03/2023 | 09/12/2024 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 143.55 | 0 | 0 | 70
10 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Laying additional pipe line with FHTC in connection with Augmentation Of Sitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000347/2024-2025 | 3300/RD/PHE | 20/11/2024 | 20/12/2024 | ZAREEN ENTERPRISE | 6.61 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Sitlagaon PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000338/2024-2025 | 3294/RD/PHE | 20/11/2024 | 04/01/2025 | M/S LUCKY CONSTRUCTION | 29.78 | 0 | 0 | 0
12 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SITALGAON Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000879/2022-2023 | 2417/MLMD | 26/09/2022 | 25/12/2022 | PABITRA MANDAL | 9.41 | 0 | 0 | 100
13 | UTTAR DINAJPUR |  | Malda Mechanical | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SITALGAON Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-02 | ORD/000880/2022-2023 | 2418/MLMD | 26/09/2022 | 25/12/2022 | JOYSHREE CONCERN | 9.38 | 0 | 0 | 100
14 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000240/2022-2023 | 373/RD/PHE | 07/02/2023 | 24/03/2023 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 0 | 100
15 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000483/2021-2022 | 178/RD/PHE | 27/01/2022 | 13/03/2022 | MAA TARA CONSTRUCTION | 111.99 | 0 | 0 | 0
16 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Soil Investigation for Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Shitlagaon W/S Scheme In Chopra Block In Uttar Dinajpur District. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000049/2022-2023 | 1236/RD/PHE | 20/06/2022 | 10/07/2022 | GEOCON INDIA | 1.98 | 0 | 0 | 100
17 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Providing FHTC in connection with augmentation of Shitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000504/2024-2025 | 49/RD/PHE | 03/01/2025 | 17/02/2025 | SANDIP SARKAR | 6.17 | 0 | 0 | 0
18 | UTTAR DINAJPUR |  | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. | SM/09990 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Shitlagaon Water Supply Scheme(Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000354/2025-2026 | 2500/RD/PHE | 12/09/2025 | 11/03/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0 | 0
Total | [13 empty] | 564.03 | 0 | 0